## Requirements - High Priority
Purina Registration Optimization
Task # | Functional Requirements | Status | Due | Owner
1 | Need a popup or prompt to get the user to opt into other brand emails if they are coming in from another brand page. (it should recognize what you are opted into already and serve up the appropriate message). | Can we track this? |  | Shannon/ Digital Team
2 | Sign-In Page: Need to determine all error states and expected user flow for "forgot password" Trigger email to: 1. reset password 2. you're in the system but need you to create your profile. Or - if the they aren't registered just pop them over to create an account | Wireframes in progress - updates due by 6/28 | 2013-06-28 | Aaron/ Shannon
3 | Need to think of way to expand the logo overlay (since there are 18+ logos) | Gabe to make update in development |  | Digital Team
4 | Sign-In Page: Need all the error messages written out (need to define all the scenarios with corresponding error states) | - Aaron compiled error message >> sent to Shannon to put into content matrix. Content Matrix due, 6/26 - Few items are pending BazaarVoice Integration | 2013-06-26 | Aaron
5 | Confirmation page – The "No Thanks" link should take the user back to their entry point (where they came from) | - Wireframes in progress - updates due by 6/28 - Update to be handled in development | 2013-06-28 | Shannon/ Digital Team
6 | Create Login URL widget – need to create (it can say login, sign in – it would change to manage profiles) | To be handled in development |  | Digital Team
7 | My News Page: the logos should not be clickable | - Wireframes in progress - updates due by 6/28 - Update to be handled in development | 2013-06-28 | Shannon/ Digital Team
8 | My News Page: Need to the think about how to format the tabs so we can add more later |  |  | Digital Team
9 | News Page: Need to create an ad service platform – static by brand for launch (will change out depending what they are opted into) |  |  | Digital Team
11 | My Info: The error messages are missing – need to understand each state and expected error messages | Aaron compiled error message >> sent to Shannon to put into content matrix. Content Matrix due, 6/26 | 2013-06-26 | Aaron/ Shannon
12 | My Info: Need to trigger confirmation email – to confirm authentic email address | - Wireframes in progress - updates due by 6/28 - Update to be handled in development | 2013-06-28 | Aaron/ Shannon
13 | My News Page: Default Ads will display (three) by default until brand choose to change them on their side. Petcentric and Purina ads should always remain | Please build this page in a way that we can display at least 10 ads. Please also build it in a way where the brand can use some of our default ads if they want, but also display their own. (Hide some/ add some) |  | Digital Team
14 | Create up to 4 variable registration fields per brand. So, each brand could add up to 4 additional fields. Are these additional fields a specific type of form element (text), or can they accommodate radio buttons, check boxes, etc? |  |  | Digital Team
15 | Default Pet Images: If user hasn't selected dog or cat, then the default dog image will display | - Wireframes in progress - updates due by 6/28 - Update to be handled in development | 2013-06-28 | Shannon/ Digital Team
16 | Creatiing an account through SSI/or default - User must confirm they are at least 18 yrs of age in order to register | - Wireframes in progress - updates due by 6/28 - Update to be handled in development | 2013-06-28 | Shannon/ Digital Team
17 | On the current User table in Janrain we have a field called CampaignCode. This field is actually the source of acquisition for a subscriber. The problem with this name is that it gets confused by everyone with our email campaign codes. Eventually we will migrate promotion history and the campaign codes into the DW, which could cause more confusion. Can we update the name of the field to “SourceCode” in Jansira? In the documentation this field is listed under the Account Creation Form Field Name:Campaigncode |  |  | Aaron/Digital Team
18 | History of source codes added to DW for subscriber records. |  | 2013-07-01 | Brandi
19 | Create Control Tables: a. Source Code: Need to define a process to adding sources to control table. If source is missing on a subscriber, record will error and not load. Need to define who will be the owner of adding source codes to mysql db. b. Registered Brand Code: control table already exists however new validation will be added to validate the brand code and error record if null |  | 2013-07-01 | Brandi
20 | Opt In Validation: Prevent users from loading a negative opt in. Set validation on the opt in fg to only pass through Y value. Users can only opt into communication via external API, it is not a source of opt out. |  | 2013-07-01 | Brandi
Task # | Creative Requirements | Status | Due | Owner
1 | Mobile Pages: Please add "BACK" button on all pages minus home page | Gabe to make update in development | 2013-07-30 | Gabe
2 |  | Gabe to make update in development. Back button should take user back to previous page in the same window | 2013-07-30 | Gabe
3 | LEGAL FEEDBACK - Sign-Up Page: copy change: Change “We’ll never post anything without your permission.” to “We’ll never post your personal or pet profile information without your permission.” | Shannon to update in wireframes and content matrix Gabe to update in developement | 2013-06-26 | Gabe/ Shannon
4 | LEGAL FEEDBACK: Unsubscribe Messages: After a user unsubscribes, they need to see/be served up a confirmation message that they have been unsubscribed. This would say/confirm, “You have been unsubscribed from <Brand>. Please allow up to 10 days for this request to take effect. | Shannon to update in wireframes and content matrix Gabe to update in developement | 2013-06-26 | Gabe/ Shannon
5 | LEGAL FEEDBACK: Unsubscribe Message: The user should also see a confirmation when all actions are taken. Something like, "Thank you, your' pet's profile has been updated." | Shannon to update in wireframes and content matrix Gabe to update in developement | 2013-06-26 | Gabe/ Shannon

## Requirements - Low Priority
Purina Registration Optimization
Task # | Functional Requirements | Status | Due | Owner
1 | Address authentication (QAS) – (did you mean this? If it's not recognized – ignore) - Phase 2
2 | The client also wants to tell the brands that if they want to add more questions to registration they can. That shouldn’t be a problem, but we need to know what those questions are, and ensure there is a place in the DB to capture that. | HOLD - Change of Scope
3
4
5
6
7
8
9